## VRP Sites Updated 6-30-26
VRP ID # | Site Name | City/Town/ County | County | Site Address | Township Range | Latitude | Longitude | Size (acres) | Contamination Type | CERCLIS # | Applicant | NMED Project Manager | Application Received | Conditional Eligibility | Public Notice | Rejection | Final Eligibility | VRA signed | Final Work Plan Received | Final Work Plan Approved | Completion Report Approval | Certificate of Completion | Conditional Certificate of Completion | Termination | Land Use Restrictions | Institutional/ Engineering Controls | Covenant Not to Sue (CNS) | Transfer CNS | Recission | Status
53011003 | Zuni San Mateo Center | Albuquerque | Bernalillo | 5555 Zuni Road SE | T10N, R3E, Sec 25 | 35.0729 | -106.5832 | 5.75 | Chlorinated hydrocarbons. |  | Zuni San Mateo, LLC | Faris | 2000-10-18 |  |  |  | 2001-01-11 |  |  |  |  | 2001-10-18 |  |  |  |  | 2001-10-18 |  |  | Closed
53131001 | Wyoming Mall | Albuquerque | Bernalillo | 2010 Wyoming Blvd NE |  | 35.1049 | -106.5503 | 6.01 | Chlorinated solvents. |  | Weingarten Realty Investors | Muus | 2013-07-02 | 2014-08-12 | 2014-08-27 |  | 2014-11-07 | 2014-12-03 | 9-Sep-13 27-Feb-14 5-Jul-14 | 2015-01-09 | 2015-01-09 |  | 2015-02-27 |  | non-residential land use; | maintain concrete slab |  |  |  | Active - CCOC
53171008 | Wirtco - 1 Hour Martinizing | Santa Fe | Santa Fe | 1091 S. St. Francis Drive | T17N, R9E, Sec 26 | 35.6746 | -105.9531 | 0.5 | Chlorinated solvents in ground water and soil vapor. |  | Wirtco Inc. | Noger | 2017-10-17 | 2017-12-01 | 2017-12-23 |  | 2018-02-27 | 2018-03-07 | 2018-10-22 | 2019-05-01 | [9 empty] | Active
53141006 | Williams Property | Albuquerque | Bernalillo | 5101 Williams St SE |  | 35.0069 | -106.6598 | 28.5 | Nitrate, petroleum hydrocarbons |  | NMT Land Investments, LLC | Morgan | 2014-10-17 | 2015-07-24 | 2015-08-07 |  | 2016-04-19 | 2016-08-10 | [5 empty] | 2026-01-07 | [5 empty] | Terminated
53141004 | Wild Wings Subdivision Lot 2 | Farmington | San Juan | 2700 E. Main |  | 36.7416 | -108.1703 | 1.2 | petroleum hydrocarbons and one PCE detect in soil |  | Mavin Capital LLC & ITE Ltd. | Furmall | 2014-07-09 | 2014-07-24 | 2014-08-04 |  | 2014-09-12 | 2014-10-17 | NA | NA | NA | 2014-10-17 |  |  |  |  | 2014-11-25 |  |  | Closed
53241003 | White Swan Laundy | Santa Fe | Santa Fe | 1368 Cerrillos Road | T17N, R9E, Section 26 | 35.67 | -105.964 | 0.6 | Chloronated solvents: PCE, TCE, DCE, vinyl chloride |  | Elisia LLLP | Morgan | 2024-07-18 | 2024-10-30 | 2024-10-30 |  | 2025-01-13 | 2025-01-22 | 2025-04-18 | 2025-04-23 | [9 empty] | Active
53063001 | White Sands Boulevard | Alamogordo | Otero | All at SEC of 10th Street and White Sands Boulevard | T16S, R10E, Sec 19 | 32.8996 | -105.9601 | 4.85 | Petroleum hydrocarbons in soil and ground water, and chlorinated solvents in groundwater. | NM000605693 | CAP II 10th/White Sands, LLC | Richards | 2006-01-23 |  |  |  | 2006-06-16 | [5 empty] | 9-Feb-2007 29-Dec-08 revised |  |  | Continued monitoring of ground water. | 21-Mar-07 29-Dec-08 revised 25-Sep-09 revised |  |  | Active - CCOC
53201002 | West Griggs- Las Cruces |  | Dona Ana | SE corner of W. Griggs Ave. and Water St. | T23S, R 2E, S 18 | 32.3094 | -106.7793 | 1.26 | PCE and daughter products |  | City of Las Cruces | Noger | 2020-07-13 | 2020-11-03 | 2020-11-13 |  | 2021-01-08 | 2021-02-04 |  |  | 2023-03-20 |  | 2024-01-09 |  | non-residential use due to PCE in shallow soil |  |  |  |  | Active - CCOC
53091002 | WESST Enterprise Center | Albuquerque | Bernalillo | 205 Roma Ave NE | T10N, R3E, Sec 17 | 35.0885 | -106.6443 | 0.4425 | Ground water contamination by PCE from off-site source. |  | WESST Corporation | Muir | 2009-10-07 | 2009-12-04 | 2010-12-21 |  | 2010-05-05 | 2010-05-18 | 2010-11-24 |  | 2011-11-09 | 2012-06-26 |  |  |  |  | 2013-06-03 |  |  | Closed
53161009 | Wellborn - DE Facility | Albuquerque | Bernalillo | 215 Rossmoor Road SW | T9N, R3E, Sec 36 | 35.0294 | -106.6603 | 61.15 | VOCs and heavy metals in soil and groundwater |  | Dunn Edwards Corporation | Richards | 2016-09-19 | 2016-09-20 | 2016-12-05 |  | 2017-01-26 | 2017-02-14 | 11/20/19 (Rec'd soil gas & indoor air work plan); 12/17/18 (Rec'd remediation work plan) | 12/21/18 (Approved soil gas & indoor air assessment work plan); 6/7/19 (Approved ground water remediation portion of work plan) | [9 empty] | Active
53161002 | Wagner Equipment | Albuquerque | Bernalillo | 4000 Osuna Road NE |  | 35.155 | -106.5967 | 25 | TPH-DRO, TPH-MRO in soils |  | Wagner Equipment Co | Richards | 2016-02-05 | 2016-03-24 | 2016-04-01 |  | 2016-06-03 | 2016-06-27 | 2016-07-07 | 2016-07-19 | 2020-02-21 | 2020-03-09 | [7 empty] | Closed
53231005 | Video Cassette Recorder Services | Farmington | San Juan | 1915 N. Butler Ave | T29N R13W Section 10 | 36.7478 | -108.1981 | 0.466 | Chlorinated solvents |  | Permco LLC | Noger | 2023-08-21 | 2023-10-24 | 2023-11-30 |  | 2024-01-09 | 2024-01-22 | 2024-04-09 | 2024-05-02 | 2024-12-02 | 2025-01-22 |  |  | none |  | 2025-01-22 |  |  | Closed
53141005 | Vehicle Maintenance Facility | Taos Ski Valley | Taos | 101 Ocean Blvd | T27N, R14E, Sec 4 | 36.5966 | -105.4596 | 0.54 | petroleum hydrocarbons in soils |  | Taos Ski Valley | Furmall | 2014-08-28 | 2014-09-26 | 2014-10-09 |  | 2014-12-03 | 2014-12-19 | 2014-08-28 | 2014-12-19 | 2015-03-20 | 2015-05-15 | [7 empty] | Closed
53101002 | US Postal Service Site | Albuquerque | Bernalillo | 3413 Broadway Blvd SE | T9N, R3E, Sec 5 | 35.0356 | -106.6479 | 42.8314 | Ground water contamination by creosote from off-site Superfund source. |  | US Food Service | Cook | 2010-02-16 | 2010-04-20 | 2010-05-28 |  | 2010-06-30 | 2010-08-02 |  |  | 2016-04-08 | 2017-02-14 | [7 empty] | Closed
53013001 | Union Pacific Railroad Alamogordo Former Tie Treating Facility | Alamogordo | Otero | vacant county land | T16S, R9E, Sec 25 | 32.8964 | -105.9661 | 18.619 | Polycyclic aromatic hydrocarbons (PAHs) in soil and ground water. | NMD986669026 | Union Pacific Railroad Co | Furmall | 2001-05-15 |  |  |  | 2001-10-22 |  |  |  |  | 2006-12-07 |  | 2010-04-05 |  |  |  |  | 2009-01-30 | Active- CCOC
53083002 | Tyrone Gun Club | Tyrone | Grant | Approx. 1 mile west of Tyrone | T18S, R14W, Sec 29 | 32.7167 | -108.3135 | 16.52 | Lead - firing range. |  | New Mexico State Land Office | Furmall | 2007-12-05 | 2008-05-05 | 2008-05-28 |  | 2008-09-23 | 2008-12-03 | 2008-09-23 | 2013-05-09 | 2013-10-21 | 2013-11-06 | [7 empty] | Closed
53083002 | Tyrone Gun Club | Tyrone | Grant | Approx. 1 mile west of Tyrone | T18S, R14W, Sec 29 | 32.7167 | -108.3135 | 16.52 | Lead - firing range. |  | New Mexico State Land Office | Furmall | 2007-12-05 | 2008-05-05 | 2008-05-28 |  | 2008-09-23 | 2008-12-03 | 2008-09-23 | 2013-05-09 | 2013-10-21 | 2013-11-06 | [7 empty] | Closed
53081003 | Truly Nolen Exterminating | Albuquerque | Bernalillo | 510 Candelaria Rd. NE | T10N, R3E, Sec 9 | 35.1161 | -106.6343 | 2 | Chlordane and heptaclor. |  | Jaynes Corporation | Muir | 2008-06-18 | 2008-11-10 |  |  | 2009-01-14 | 2009-02-03 |  |  | 2009-02-19 | 2009-02-26 |  |  |  |  | 2009-04-06 |  |  | Closed
53021004 | Triple S, Inc. (Kerr McGee Number #6007) | Albuquerque | Bernalillo | 322 Louisiana Boulevard SE | T10N, R4E, Sec 30 | 35.0728 | -106.5686 | 0.3 | Petroleum hydrocarbons. |  | Triple S, Inc. | Mariano | 2001-11-13 |  |  |  | 2002-05-15 |  |  |  |  | 2002-07-22 |  |  |  |  | 2005-04-04 |  |  | Closed
53112001 | Trinity Redevelopment | Los Alamos County | Los Alamos | 901 Trinity Drive |  | 35.8792 | -106.2944 | 15 | Various. |  | Los Alamos County | Cook | 2011-07-13 | [10 empty] | 2015-08-14 | [5 empty] | Closed
53041004 | Thriftway- Wright Gallery | Albuquerque | Bernalillo | 2130, 2104, 2108 San Mateo Blvd | T10N, R3E, Sec 13 | 35.1013 | -106.5861 | 0.32 | Petroleum hydrocarbons. |  | Thriftway Marketing, Corp. | Bascomb | 2004-05-14 |  |  |  | 2005-02-02 |  |  |  |  | 2005-08-18 |  |  |  |  | 2005-08-18 |  |  | Closed
53044001 | Tastee Freez, Roswell | Roswell | Chaves | 1303 W. Second St. | T10S, R24E, Sec 32 | 33.3947 | -104.54 | 0.89 | PCE, TCE. |  | Mr. and Mrs. Owen & Mrs Angelos | Bascomb | 2003-08-29 |  |  |  | 2003-12-03 |  |  |  |  | 2005-04-25 |  |  |  |  | 2005-04-25 |  |  | Closed
53083003 | Sun Valley Do it Center | Silver City | Grant | 1401 Silver Heights Boulevard | T17S, R14W, Sec 34 | 32.7802 | -108.2746 | 1.13 | Chlorinated hydrocarbon contamination in the subsurface soil, specifically PCE. |  | Mr. Roy and Mrs. Mary Chavez | Muir | 2008-04-23 | 2008-06-03 | 2008-06-19 |  | 2008-07-17 | 2008-08-11 |  |  | 2008-07-25 | 2008-07-24 |  |  |  |  | 2008-07-24 |  |  | Closed
53021001 | Sun Country Industries | Albuquerque | Bernalillo | 9421 Coors Road NW | T11N, R3E, Sec 18 | 35.1876 | -106.6618 | 1.76 | Solvents (potential volatile organic compounds). |  | Michelson Family Ltd Prtn. | Mariano | 2001-07-31 |  |  |  | 2003-02-04 |  |  |  |  | 2003-11-10 | [7 empty] | Closed
53061006 | Storage Systems, LLC | Albuquerque | Bernalillo | Lots 30, 31 and 32 Block 4 of Tract A Unit B of N. Albuquerque Acres | T11N, R3E, Sec 12 | 35.1951 | -106.5856 | 2.45 | Municipal solid waste. |  | Storage Systems, LLC | Bascomb | 2006-06-13 |  |  |  | 2007-02-19 |  |  |  |  | 2008-04-15 |  |  |  |  | 2008-06-20 | 2016-05-06 |  | Closed
53094002 | Starlight Drive In Theatre | Roswell | Chaves | 1901 SE Main (US Hwy 285) | T11S, R24E, Sec 9 | 33.3683 | -104.5142 | 19.28 | Ground water contamination by PCE from off-site source. | EPA ill: NM0000605386 | Michael Shyne | Swanson | 2009-06-03 |  |  | 2011-04-25 | [13 empty] | Closed
53103001 | Stanco Metal Products | Santa Teresa | Doña Ana | 301 Avenida de Ascencion | T29S, R2E, Sec 13 | 31.7885 | -106.6895 | 2.515 | Petroleum hydrocarbons in soil. |  | Verde Border One and Two LLC | Furmall | 2010-04-05 | 2010-08-19 |  |  | 2013-05-31 | 2013-06-06 | 2010-06-26 | 2010-08-10 | 2013-06-28 | 2013-09-05 | [7 empty] | Closed
53131002 | Smith's #491 Fuel Center | Santa Fe | Santa Fe | 800 St. Michael's Drive | Santa Fe Grant | 35.6589 | -105.963 | 2.1 | TPH-DRO, TPH-ORO in soil |  | Smith's Food and Drug Stores | Furmall | 2013-09-04 | 2013-11-07 | 2014-01-10 |  | 2014-04-11 | 2014-05-02 | 2014-07-11 | 2014-07-21 | 2015-03-06 | 2015-05-15 |  |  |  |  | 2015-09-25 |  |  | Closed
53021007 | Serna Trucking | Albuquerque | Bernalillo | 480 Sunset Road | T10N, R3E, Sec 19 | 35.0754 | -106.676 | 15 | Petroleum hydrocarbons. |  | Bernalillo County | Sims | 2002-02-07 |  |  |  | 2002-07-26 |  |  |  |  | 2002-10-10 |  |  |  |  | 2002-12-18 |  |  | Closed
53051001 | Schwartzman Tract C-3-A | Bernalillo County | Bernalillo | NE of Prince Rd and Rio Bravo Blvd | T9N, R3E, Sec 8 | 35.0273 | -106.6519 | 3.1764 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-28 |  |  |  |  | 2007-05-21 |  |  | Closed
53051001 | Schwartzman Tract C-2-A | Bernalillo County | Bernalillo | 500ft from NW corner Rio Bravo/Broadway | T9N, R3E, Sec 8 | 35.029 | -106.6508 | 31.191 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-30 |  |  |  |  | 2007-03-30 |  |  | Closed
53101003 | Schwartzman Tract C-1-A-1-A | Albuquerque | Bernalillo | 3750 Prince Street | T9N, R3E, Sec 5 | 35.0312 | -106.6507 | 24.39 | Various. |  | BMR Funding LLC | Homer | 2010-04-16 | 2011-10-10 | 2011-11-17 |  | 2012-02-10 | 2012-03-01 | 2-May-12 2-Nov-12 | 14-May-12 6-Nov-12 | 2013-01-22 | 2013-02-15 | [7 empty] | Closed
53051001 | Schwartzman Tract B | Bernalillo County | Bernalillo | NW of Prince Rd and Rio Bravo Blvd | T9N, R3E, Sec 5 | 35.0293 | -106.6536 | 26.173 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-28 |  |  |  |  | 2007-05-21 |  |  | Closed
53051001 | Schwartzman Tract 5 | Bernalillo County | Bernalillo | E. of Broadway/appx 1,125 ft N. of Rio Bravo | T9N, R3E, Sec 5, 8 | 35.0343 | -106.6453 | 13.71 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53051001 | Schwartzman Tract 28 | Bernalillo County | Bernalillo | W. of I-25/N.of Tract4 | T9N, R3E, Sec 5 | 35.0413 | -106.6401 | 1.87 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53051001 | Schwartzman Tract 17 | Albuquerque | Bernalillo | W. of 2nd Street/appx. 750 ft S. Woodward RD | T10N, R3E, Sec 32 | 35.0479 | -106.656 | 6.92 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-04-13 |  |  |  |  | 2007-04-13 |  |  | Closed
53051001 | Schwartzman Tract 16 | Bernalillo County | Bernalillo | E of Barr Canal/W.of Albu. Riverside Drain | T10N, R3E, Sec 31 | 35.0445 | -106.661 | 126.47 | Petroleum hydrocarbons, chlorinated solvents, creosote, nitrate. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-06-27 |  |  |  |  | 2008-05-06 |  |  | Closed
53061007 | Schwartzman Tract 15 | Albuquerque | Bernalillo | 3301 Second St. SW | T9N, R3E, Sec 5 | 35.0392 | -106.6565 | 45.5 | Petroleum hydrocarbons, creosote, iron and manganese, chlorinated solvents, PCBs, pesticides. |  | Schwartzman, Inc | Muir | 2006-06-15 |  |  | 2009-12-23 | [13 empty] | Closed
53051001 | Schwartzman Tract 14S | Bernalillo County | Bernalillo | NE corner of 2nd Street & Rio Bravo Blvd | T9N, R3E, Sec 5 | 35.0281 | -106.6566 | 30.8045 | Petroleum hydrocarbons, chlorinated solvents, creosote. |  | Schwartzman, Inc | Bascomb | 2004-07-19 |  |  |  | 2005-09-29 |  |  |  |  | 2007-03-09 |  |  |  |  | 2007-03-09 |  |  | Closed
53041001 | Schwartzman Inc, Tract 2 | Bernalillo | Bernalillo | Rio Bravo & Broadway | T9N, R3E, Sec 8 & 9 | 35.0234 | -106.6471 | 8.3 | Petroleum hydrocarbons. |  | Schwartzan, Inc. | Bascomb | 2003-08-18 |  |  |  | 2003-10-31 |  |  |  |  | 2003-11-21 |  |  |  |  | 26-Nov-03 4-Jun-08 |  |  | Closed
53041001 | Schwartzman Inc, Tract 1 | Bernalillo | Bernalillo | Rio Bravo & I-25 | T9N, R3E, Sec 8 & 9 | 35.0229 | -106.6432 | 51.76 | Petroleum hydrocarbons. |  | Schwartzan, Inc. | Bascomb | 2003-08-18 |  |  |  | 2003-10-31 |  |  |  |  | 2003-11-21 |  |  |  |  | 26-Nov-03 13-Jun-08 |  |  | Closed
53032001 | Santa Fe Rail Yard Properties | Santa Fe | Santa Fe | Santa Fe Rail Yard | T17N, R9E, Sec 23 | 35.6799 | -105.9503 | 49 | Metals & petroleum hydrocarbons in soil. |  | City of Santa Fe | Mariano | 2003-02-01 |  |  |  | 2003-10-03 |  |  |  |  | 2006-02-27 |  |  |  |  | 2006-03-31 |  |  | Closed
53092001 | Santa Fe County Judicial Complex | Santa Fe | Santa Fe | 327 Sandoval St | Land Grants, Civil Colonies | 35.6849 | -105.9434 | 2.35 | Petroleum hydrocarbons in soil and ground water. |  | Santa Fe County | Richards | 2009-04-29 | 2010-08-06 | 2010-08-25 |  | 2014-05-09 | 2014-07-14 | 2015-02-16 | 2015-02-23 | 2016-02-19 |  | 2016-02-26 | [6 empty] | Active - CCOC
53041005 | Sandia Battery | Bernalillo | Sandoval | Tract 5, Bernalillo Industrial Subdivision | T12N, R4E, Sec 7 | 35.2931 | -106.5558 | 2 | Lead. | NM0001899913 | Bernalillo Development Corporation | Richards | 2004-06-02 | 2005-05-19 | 2011-02-10 |  | 2006-03-22 | 2006-04-12 | 2009-08-26 | 2010-08-18 | 2014-06-20 |  | 2014-06-27 |  | land use restricted to industrial/commercial | asphalt cap, concrete gutters, retention pond |  |  |  | Active - CCOC
53012001 | Sanbusco Market Center | Santa Fe | Santa Fe | 560 Montezuma Avenue | T17N, R9E, Sec 13 | 35.6853 | -105.9467 | 4.7985 | Hydraulic oil. |  | Sanbusco Corp. | Bynum | 2001-06-07 |  |  |  | 2001-07-15 |  |  |  |  | 2001-07-23 | [7 empty] | Closed
53011007 | San Miguel Shopping Center | Socorro | Socorro | 913 California Street (3 separate parcels) | T10N, R3E, Sec 19 | 34.0676 | -106.8932 | 2.99 | Petroleum hydrocarbons. |  | David Boggs | Mariano | 2001-06-19 |  |  |  | 2001-10-22 |  |  |  |  | 2002-04-02 |  |  |  |  | 2002-04-04 |  |  | Closed
53085003 | San Juan Spring Co. East | Farmington | San Juan | 409 E. Broadway St. | T29N, R13W, Sec 15 | 36.7282 | -108.201 | 1.29 | Dissolved chromium in ground water and petroleum hydrocarbons in soil. |  | San Juan Spring Co. | Homer | 2008-01-10 |  |  | 2014-08-29 | [13 empty] | Closed
53085001 | SAMCO Associates | Socorro | Socorro | 915 N. California Street | T22S, R3E, Sec6 | 34.0681 | -106.8933 | 0.364 | Petroleum hydrocarbons. |  | SAMCO Associates/David Boggs | Muir | 2008-09-23 | 2008-05-06 | 2008-05-31 |  | 2008-09-23 | 2008-11-07 |  |  | 2009-04-21 | 2009-05-08 |  |  |  |  | 2009-06-23 |  |  | Closed
53211001 | Sagebrush Substation | Albuquerque | Bernalillo | NE of Intersection of Sunport Blvd & University Blvd | T10, R3E, S33 | 35.0506 | -106.6283 | 20.8778 | VOCs, SVOCs, RCRA metals in soil |  | Public Service Company of NM (PNM) | Morgan | 2021-07-21 | 2022-04-19 | 2022-06-15 |  | 2022-09-19 | 2023-01-25 | Revised preliminary workplan 16-Jul-21 | 2023-01-03 | 2024-01-12 | 2024-01-12 | [7 empty] | Closed
53181003 | Rueggli/Lift 1 Site | Taos Ski Valley | Taos | 5 Firehouse Road | T27N R14E, Sec 4 | 36.5963 | -105.4542 | 0.48 acres Rueggli, 0.10 acres Lift 1 site | VOCs and SVOCs typical of diesel fuel/degraded gasoline in soils |  | Taos Ski Valley | Noger | 2018-08-13 | 2018-10-29 | 2018-11-08 |  | 2019-01-24 | 2019-02-14 |  | 2019-01-24 | 2021-09-01 | 2024-02-13 | 2024-02-13 |  | non-residential use due to TPH in soil unerneath Lift 1 area |  |  |  |  | Active - CCOC
53151003 | Ritter Investments | Roswell | Chaves | 400 E. College Blvd. |  | 33.4085 | -104.5176 | 4.3 | BTEX, naphthalenes, arsenic, lead |  | Ritter Investments LLC | Morgan | 2015-07-24 | 2016-02-15 | 2016-03-11 |  | 2016-05-02 | 2016-05-16 | 2019-08-29 | 2019-11-19 | [9 empty] | Terminated
53221002 | Red Planet Storage | Roswell | Chaves | 12 Petro Drive | T10S, R24E Sec 33 | 33.407 | -104.517 | 7.821 | Total Petroleum Hydrocarbons, volatile organic compounds, semi-volatile organic compounds, polycyclic aromatic hydrocarbons, RCRA Metals, 1,2-dibromoethane |  | Red Planet, LLC | Morgan | 2022-02-07 | 2022-03-31 | 2022-03-09 |  | 2022-06-27 | 2022-09-19 | 2022-09-23 | 2022-10-04 | [9 empty] | Active
53021003 | Ramsey Oil | Grants | Cibola | 210 W. Santa Fe Avenue | T11N, R10W, Sec 25 | 35.1498 | -107.849 | 56 | Petroleum hydrocarbons. |  | BNSF Railway Co. | Cook | 2001-09-28 | 2001-10-22 | 2001-11-14 |  | 2002-01-03 | 17-Jan-02 9-Aug-17 | 2016-09-01 | 2002-01-17 | 2018-01-26 |  | 2018-08-24 |  | land use retricted to non-residential & prohibition of construction of wells into the water bearing zone - administered through NM Office of State Engineer. |  |  |  |  | Active-CCOC
53231001 | Quinn Tire | Santa Fe | Santa Fe | 1005 Cordova Road |  | 35.6751 | -105.9517 | 0.43 | Petroleum in soil, chlorinated solvents in soil vapor |  |  | Cook | 2023-01-20 | 2023-04-04 | 2023-05-26 |  | 2023-07-31 | 2023-09-11 | 2023-05-11 | 2023-08-28 | 2024-05-02 | 2024-09-30 | [7 empty] | closed
53161006 | Quality Pontiac Tract 1 | Albuquerque | Bernalillo | 1300 Lomas Blvd. NE | T10N, R3E, SE 1/4 Sec 16 | 35.091 | -106.629 | 4.974 | petroleum hydrocarbons in shallow soil |  | Sandia Foundation | Cook | 2016-06-30 | 2016-07-29 | 2016-09-09 |  | 2016-10-28 | 2016-12-09 | 2016-11-07 | 2017-01-27 | 2017-01-27 | 2016-12-09 | [7 empty] | Closed
53001001 | Proposed Forest Service Facility | Albuquerque, Bernalillo County | Bernalillo | 333 Broadway Boulevard SE | T10N, R3E, Sec 20 | 35.0814 | -106.6468 | 3.3994 | Petroleum hydrocarbons. |  | Aardex Corp. | Novick | 1999-08-12 |  |  |  | 1999-12-08 |  |  |  |  | 2000-02-07 |  |  |  |  | 2000-02-07 |  |  | Closed
53171005 | ProBuild Millworks Facility (former) | Albuquerque | Bernalillo | 6700 Bluewater Road |  | 35.0852 | -106.7143 | 7 | chlorinated solvents in subsurface soils, soil vapor, indoor air |  | ProBuild Real Estate Holdings, LLC | Muus | 2017-07-14 | 2017-10-04 | 2017-10-18 |  | 2017-12-21 | 2018-01-26 | 2018-03-28 | 2018-04-20 | 2018-10-23 | 2018-12-31 |  |  |  |  | 2019-03-11 |  |  | Closed
53061004 | Price's Valley Gold North Dairy - North Area | Rio Rancho | Sandoval | 618 Highway 528 | T13N, R3E, Sec 25 | 35.3194 | -106.5742 | 86.2 | Nitrogen compounds in soil. |  | Valley Gold Farms | Bascomb | 2005-11-21 | 2006-03-22 |  |  | 2006-06-28 | 2006-07-12 | 2006-07-11 | 2006-07-28 | 2006-09-25 | 2006-11-28 |  |  |  |  | 16-Mar-07 17-Jan-08 9-Apr-08 2-Feb-14 | 30-Nov-10 27-Dec-11 |  | Closed
53062001 | Premier Nissan | Santa Fe | Santa Fe | 2005 St. Michael's Drive | T17N, R9E, Sec 34 | 35.6596 | -105.9663 | 2.9 | Petroleum hydrocarbons associated with hydraulic lifts and sump. |  | Omega Automotive Real Estate, LLC | Bynum | 2006-04-06 |  |  |  | 2006-05-31 |  |  |  |  | 2006-06-02 |  |  |  |  | 2006-06-02 | 2010-10-22 |  | Closed
53051002 | Ponderosa Products - Lots 1 and 2 | Albuquerque | Bernalillo | 1701 Bellamah Ave | T10N,R3E, Sec 7 | 35.1045 | -106.6631 | 7.48 | Petroleum hydrocarbons, formaldehyde. |  | Saw Mill Community Land Trust | Shean | 2004-10-19 |  |  |  | 2005-05-06 |  |  |  |  | 2009-09-22 |  |  |  |  | 2009-12-28 |  |  | Closed
53131004 | Plaza Maya | Albuquerque | Bernalillo | 615 First St. NW | T10N, R3E, Sec 17 | 35.0897 | -106.6471 | 1.27 | Petroleum hydrocarbons |  | SFGVI - NM, LLC | Morgan | 2013-11-13 | 2013-12-30 | 2024-01-15 |  | 2014-02-20 | 2014-02-24 | [11 empty] | Active
53151002 | Piñon Square | Albuquerque | Bernalillo | 7849 Tramway Blvd NE |  | 35.1736 | -106.497 | 1 | PCE, TCE in soil and air |  | 7849 Tramway Blvd NE LLC | Richards | 2015-07-16 | 2015-11-03 | 2015-11-30 |  | 2016-01-29 | 2016-01-29 | 2016-04-07 | 2016-05-26 | 2020-12-11 | 2025-03-31 | 2021-08-24 | [6 empty] | closed
53072001 | Phillips Petroleum | Santa Fe | Santa Fe | 760 Cerrillos Road | T17N, R9E, Sec 26 | 35.6792 | -105.9509 | 0.39946 | Petroleum hydrocarbons in soil and groundwater; pce contamination in groundwater. |  | City of Santa Fe | Brooks | 2007-04-03 |  |  |  | 2007-08-21 |  |  |  |  | 2009-12-18 | [7 empty] | Closed
53023002 | Peru Hill Mill | Deming | Luna | Vacant county land | T23S, R9W, Sec 18 & 19, part of Sec 17 & 20 | 32.3036 | -107.81 | 1479.34 | Metals. | NMD07119986 | City of Deming | Muus | 2002-02-26 |  |  |  | 2003-04-30 | 2003-07-15 |  |  | 2009-02-27 |  | 2010-03-04 |  | Land use restricted to industrial/commercial use. | Former tailings areas have fencing and engineered cap requiring semi-annual inspections and maintenance as needed. Ground water monitoring in 2016 and 2021. | 2010-03-14 |  |  | Active - CCOC
53161003 | Park Avenue Cleaners - SF | Santa Fe | Santa Fe | 720 St. Michaels Drive, Suite K | T17N, R9E, Sec 35 | 35.6577 | -105.9612 | 6.577 | PCE in sub-slab soils |  | Del Sol Shopping Center Partners | Muus | 2016-02-22 | 2016-03-25 | 2016-04-08 |  | 2016-06-03 | 2016-06-27 | 7/8/2016 11/19/2016 | 2016-07-25 | 2020-12-04 |  | 2021-07-08 | [6 empty] | Active-CCOC
53001004 | Park Avenue Cleaners | Albuquerque | Bernalillo | 1006 Park Avenue SW | T10N, R3E, Sec 20 | 35.0853 | -106.6594 | 0.16 | Chlorinated solvents. |  | Jonathan Siegel | Bynum | 2000-04-07 |  |  |  | 2000-10-31 |  |  |  |  | 2000-12-19 |  |  |  |  | 2000-12-20 |  |  | Closed
53031006 | Palo, Verde, Ltd. Belen | Belen | Valencia | 1304 South Main Street | T5N, R2E, Sec 19 | 34.6414 | -106.7803 | 6.3007 | Petroleum hydrocarbons. |  | Palo Verde, Ltd. | Shean | 2003-04-22 |  |  |  | 2003-06-05 |  |  |  |  | 2003-08-06 |  |  |  |  | 2003-08-15 |  |  | Closed
53024001 | O'Neal Family Trust/Gateway Subdivision | Carlsbad | Eddy | 1108 West Pierce St. | T21S, R26E, Sec 36 | 32.4364 | -104.24 | 1.33 | Petroleum hydrocarbons. |  | O'Neal Family Trust | Cook | 2002-03-21 |  | 2002-07-05 |  | 2002-08-12 | 2002-12-02 | [5 empty] | 2018-01-31 | [5 empty] | Closed
53081002 | Oakland Avenue Landfill | Albuquerque | Bernalillo | 6114 Oakland Avenue NE | T11N, R3E, Sec 13 | 35.1859 | -106.5758 | 17.39 | Muncipal solid waste. |  | Vandy Investments, Inc. | Muir | 2008-03-21 | 2008-05-13 |  |  | 2008-12-23 | 2009-02-04 |  |  | 2009-04-30 | 2009-06-23 |  |  |  |  | 2009-07-25 |  |  | Closed
53091001 | North I-25 Corp Center aka Philips Site | Albuquerque | Bernalillo | 9201 Pan American Freeway NE | T11N, R3E, Sec 12 | 35.191 | -106.5848 | 59.662 | Historic landfill, chlorinated solvents. |  | Reid and Associates, LLC | Cook | 2008-11-25 | 2009-04-10 |  |  | 2009-12-28 | 2-Aug-10 3-May-17 |  |  | 2018-02-05 |  | 2019-07-08 |  |  | Vapor mitigations system in easement |  |  |  | Active - CCOC
53001002 | Nine Mile Hill Landfill | Bernalillo County | Bernalillo | I-40 & Paseo de Vulcan | T10N, R2E, Sec 30 | 35.0735 | -106.7744 | 48 | Solid waste landfill. |  | Bernalillo County | Mariano | 1999-10-20 |  |  |  | 2000-04-27 |  |  |  |  | 2002-10-01 | [7 empty] | Closed
53161001 | New Mexico Terminal Service (former Cal-Maine) | Albuquerque | Bernalillo | 9615 Broadway SE | T8N, R3E, Sec 6 | 34.9544 | -106.6688 | 65 | nitrate, TDS, chloride, sulfate in groundwater |  | KP Wildcat LLC | Cook | 2016-02-04 | 2016-05-02 | 2016-05-13 |  | 2016-09-13 | 2017-01-19 | 2017-06-06 | 2017-07-31 |  |  |  | 2023-08-22 | [5 empty] | Terminated
53171006 | Mt. Chalchihuitl and Cerrillos Gravel Products | Cerrillos | Santa Fe | Cerrillos Hills Mining District | T14N, R8E, Sec 4,5,8 and T15N, R8E, Sec 33 | 35.4703 | -106.1125 | 678 | metals in soil, particularly antimony, arsenic, cadmium, copper, lead, thallium, and zinc |  | Santa Fe County | Muus | 2017-08-14 | 2017-10-16 | 2017-10-20 | [13 empty] | 2020-09-08 | closed-incomplete
53102001 | Mills Plaza Shopping Center | Las Vegas | San Miguel | 254 Mills Avenue | T16N, R16E, Sec 22 | 35.6 | -105.2331 | 6.96 | PCE from dry cleaning. | NMD982555625 | Mills Acquisition Co. LLC | Muir | 2010-04-07 | 2010-07-22 | 2010-08-06 |  | 2010-10-08 | 2010-11-05 | 2010-10-26 |  | 2011-10-28 | 2012-07-06 |  |  |  |  | 2014-01-10 |  |  | Closed
53231004 | MI Swaco-Hobbs | Hobbs | Lea | 7714 N. Lovington Hwy |  | 32.7893 | -103.2084 | 9.18 | Petroleum & metals in soil |  | Schlumberger | Noger | 2023-04-13 | 2023-07-31 | 2023-12-15 |  | 2024-04-26 | 2024-04-26 | 2024-05-02 | 2024-05-28 | 2025-01-11 |  | 2025-03-03 |  | restricted to non-residential use due to Arsenic and Barium in soil below Industrial SSL's | non-residental use only | 2025-03-03 |  |  | CCOC
53211003 | MI SWACO - Farmington | Farmington | San Juan | 3601 Bloomfield Hwy | T29 R13W Sec24 | 36.7187 | -108.1648 | 1.3 | TPH, RCRA Metals |  | MI LLC | Cook | 2021-09-16 | 2022-04-19 | 2022-05-30 |  | 2022-08-05 | 2022-09-19 | 2022-08-31 | 2023-01-20 | 2023-09-11 | 2024-05-07 |  |  | Non residential land use. Further excavation requires management in accordance with a Petroleum Contaminated Soil Contingency Plan. |  |  |  |  | Active - CCOC
53022001 | Medite Corp., Las Vegas Div. | Las Vegas | San Miguel | U.S. Highway 85 | T16N, R17E, Sec 6 | 35.6458 | -105.1833 | 78.11 | Petroleum hydrocarbons. |  | Medite Corp. | Bascomb | 2002-04-29 |  |  |  | 2003-10-29 |  |  |  |  | 2004-02-17 | [7 empty] | Closed
53011001 | McGehee & Assoc. | Gallup | McKinley | Vacant land SE of Lincoln & 11th St | T15N, R18W, Sec 16 | 35.5313 | -108.758 | 5.13 | Petroleum hydrocarbons. |  | McGehee & Assoc. | Bynum | 2000-06-22 |  |  |  | 2000-10-02 |  |  |  |  | 2000-11-06 |  |  |  |  | 2000-11-07 |  |  | Closed
53151004 | McAnally Enterprises (Las Cruces Community Farms) | Berino | Doña Ana | 415 San Benito Road | T26S, R3E, 1/4NW, 1/4SE | 32.0718 | -106.6215 | 250 | nitrate-N, chloride, sulfate, TDS in ground water. |  | Las Cruces Community Farms, LLC | Morgan | 2015-08-27 | 2015-11-03 | 2015-11-13 |  | 2015-12-23 | 2016-01-29 | 2016-03-30 | 6/10/2016 (conditional approval) | [9 empty] | Terminated
53121003 | Mast Voyager Tract | Albuquerque | Bernalillo | NWC of Transport ST SE and Sunport Blvd SE |  | 35.0495 | -106.6362 | 12.68 | Lead in soil, volatile organic compounds in ground water. |  | Thomas Macken | M. Hunter | 2012-03-13 | 2012-08-03 | 2012-08-14 |  | 2012-12-28 | 2013-01-22 | 2013-01-04 | 2013-01-28 | 2013-02-21 | 2013-04-09 |  |  |  |  | 2014-03-28 |  |  | Closed
53151001 | Marble-Arno Property | Albuquerque | Bernalillo | 830 Broadway Blvd NE |  | 35.0913 | -106.6424 | 2.1 | Residual TPH in soil; dissolved Fe and Mn in ground water. |  | City of Albuquerque | Cook | 2015-07-01 | 2015-07-29 | 2015-08-07 |  | 2015-11-17 | 2015-10-09 | 2015-09-22 | 2015-10-09 | 2016-05-13 |  | 2016-05-24 |  | non-residential land use. |  |  |  |  | Active - CCOC
53231006 | Main & Valle Vista | Farmington | San Juan | 2701 West Main Street | T29, R13 W | 36.7327 | -108.2444 | 2.51 | TPH |  | Mav Farmington | Morgan | 2023-12-13 | 2024-02-12 | 2024-02-27 |  | 2024-05-28 | 2024-05-28 | 2024-05-31 | 2024-06-12 | 2024-07-31 | 2024-07-31 |  |  | None | None | 2024-09-20 |  |  | Closed
53171001 | Loving Salt | Malaga | Eddy | 1615 Pecos Highway (may be 1624 Pecos Highway) | T24S, R28E, Sec 19 | 32.2237 | -104.0729 | 2.38 | chloride and TDS |  | RK Pump & Supply | Muus | 2017-01-17 | 2018-01-16 | 2018-03-08 | 2018-09-06 | [13 empty] | Application denied
53171003 | Legacy Hospitality Central | Albuquerque | Bernalillo | 222 Central Avenue SE | T10N, R3E, Sec 20 | 35.0833 | -106.645 | 0.814 | hydrocarbons in groundwater from offsite source |  | FBC II, LLC | Muus | 2017-05-03 | 2017-07-19 | 2017-07-28 |  | 2017-09-15 | 2018-01-04 |  | 2018-07-20 | 2018-07-20 |  | 2018-09-24 |  |  |  | 2018-12-20 |  |  | ActIve- CCOC
53241001 | La Unica #1 | Santa Fe | Santa Fe | 647 Cerrillos Rd. | T17N R9E S26 | 35.6802 | -105.9474 | 0.36 | Chlorinated hydrocarbons. |  | La Unica Dry Cleaners & Alterations #1 | Morgan | 2024-04-12 | 2024-07-29 | 2024-09-15 |  | 2024-12-02 | 2024-12-09 | 2026-01-27 | 2026-05-26 | [9 empty] | Active
53023001 | L & P Properties | Las Cruces | Doña Ana | 300 N. Archuleta | T23S,R1E, Sec 13 | 32.305 | -106.7958 | 1.27 | Petroleum hydrocarbons. |  | Paul Buldain | Muir | 2001-08-30 | 2001-12-19 | 2002-01-03 |  | 2002-02-13 | 2002-04-04 |  |  | 2010-06-04 | 2010-11-30 | [7 empty] | Closed
53161004 | Kmart Store #7017 | Roswell | Chaves | 1705 S. Main Street | T15N, R24E, Sec 9 | 33.3714 | -104.5215 | 4.98 | petroleum hydrocarbons and metals |  | Sears Holdings Management Corporation | Cook | 2016-05-02 | 2016-06-17 | 2016-07-12 |  | 2016-08-29 | 2016-09-14 | 2016-10-07 | 2016-11-14 | 2016-11-14 | 2017-03-23 | [7 empty] | Closed
53201003 | Kachina Maintainence Facility |  | Taos | Kachina Base, Taos Ski Vally, end of Kachina Rd. | T27N R14E, Sec 15 (projected) | 36.3438 | -105.2622 | 0.1 | Petroleum hydrocarbons in soil & groundwater |  | Taos Ski Valley | Cook | 2020-12-04 | 2021-02-11 | 2021-02-26 |  | 2021-08-26 | 2021-08-30 | 2021-08-30 | 2022-01-07 | 2023-01-19 | 2024-02-13 |  |  | Non residential land use. Further excavation requires management in accordance with a Petroleum Contaminated Soil Contingency Plan. |  |  |  |  | Active - CCOC
53114001 | International Isotopes | Lea County | Lea |  | T18S, 36E, Sec 27 | 32.7186 | -103.3422 | 640 | Sulfate, chloride, TDS - trespassing ground water plume from Excel subsidiary. |  | Lea County | Muir | 2010-11-30 | 2011-04-26 | 2011-05-06 |  | 2011-06-17 | 2011-06-27 | 2011-06-30 |  | 2011-07-21 | 2011-07-21 |  |  |  |  | 2011-12-08 |  |  | Closed
53083001 | Inspiration Heights | Las Cruces | Doña Ana | 7805 Arroyo Avenue | T22S, R3E, Sec 6 | 32.4177 | -106.6826 | 135 | Petroleum hydrocarbons and total nitrates in soil and ground water. |  | Pacific Holt Corporation | Muir | 2004-06-22 | 2008-05-06 |  |  | 2008-11-20 | 2009-01-28 |  |  | 2009-04-13 | 2009-04-15 |  |  |  |  | 2009-05-19 |  |  | Closed
53141008 | Imperial Building (aka Hyder Property) | Albuquerque | Bernalillo | 205 Silver SW - Block 23, Lots 13 - 24, Original Townsite, Bernalillo County, NM | T10N,R3E, Sec 20 | 35.0826 | -106.6501 | 1.1 | chlorinated solvents and petroleum in soil vapor and soil |  | City of Albuquerque/UR 205 Silver, LLC | Muus | 2014-12-10 | 2015-01-13 | 2015-01-27 |  | 2016-08-04 | 2016-09-23 | 2016-01-28 | 2016-09-30 | 2016-10-17 | 2016-11-04 | [7 empty] | closed
53051003 | Hyder Property | Albuquerque | Bernalillo | Block 23, Lots 13 - 24, Original Townsite, Bernalillo County, NM | T10N,R3E, Sec 20 | 35.0826 | -106.6501 | 1 | Potential lead contaminated surface soils, volatile and semi-volatile organic compounds in subsurface. |  | City of Albuquerque | Shean | 2004-11-09 |  |  |  | 2005-03-22 |  |  |  |  | 2005-05-27 | [7 empty] | Closed
53094001 | Hotel Clovis | Clovis | Curry | 201 N. Main Street | T2N, R36E, Sec 18 | 34.3998 | -103.2051 | 1.37 | Asbestos, lead paint, mold, pigeon droppings. |  | City of Clovis | Muir | 2008-12-15 | 2009-03-13 |  |  | 2010-04-05 | 2011-12-12 |  |  | 2011-12-14 | 2011-12-23 | [7 empty] | Closed
53003001 | Hop Canyon/Waldo Mill | Socorro County | Socorro | 1.2 miles south of Magdalena | T2S, R4W, Sec 34, 35 | 34.0929 | -107.2265 | 225 | Metals. | NMD981600455 | Asarco | Muir | 2000-03-20 |  |  |  | 2000-06-29 | [12 empty] | Closed
53171004 | Homewood Suites | Albuquerque | Bernalillo | 5400 San Antonio | T11N, R3E, Sec25 | 35.1588 | -106.5848 | 1.98 | Historic landfill |  | Mtn West Lodging | Cook | 2017-07-05 | 2017-10-06 | 2017-10-23 |  | 2018-01-30 | 2018-02-19 | 2017-09-06 | 2018-02-08 | 2020-03-02 |  | 2021-07-02 | [6 empty] | Active-CCOC
53081004 | Holiday Park Cleaners | Albuquerque | Bernalillo | 2917 Juan Tabo NE | T10N, R4E, Sec 9 | 35.1151 | -106.5158 | 5 | Tetrachloroethene (PCE) in soil. |  | William and Glenda Quint | Muir | 2008-05-09 | 2008-08-01 | 2008-09-23 |  | 2008-11-21 | 2008-12-23 |  |  | 2009-01-13 | 2009-01-14 | [7 empty] | Closed
53044003 | Gnome-Coach | Carlsbad | Eddy | 25 miles east of Carlsbad, Eddy County, New Mexico | T23S, R30E, Sec 31 | 32.263 | -103.867 | 680 | Radiological / diesel contamination of surface soils. | NM8890116132 | DOE Legacy Management | Richards | 2004-05-12 | 2004-07-15 | 2004-08-25 |  | 2004-10-08 | 2005-06-22 |  |  | 2006-01-27 |  | 2014-09-25 |  | Ranching. | Maintain cap over shaft and drilling exclusion within 40 ft. No drilling/excavating anywhere onsite below 20 ft. Signage around perimeter and at road crossings. |  |  |  | Active - CCOC
53042001 | Gasbuggy | Rio Arriba County | Rio Arriba | Appx. 25 miles from Dulce, NM in the Carson National Forest | T29N, R4W, Sec 36 | 36.6779 | -107.209 | 20 | Petroleum hydrocabons (diesel in drilling mud). |  | DOE Legacy Management | Morgan | 2004-04-27 | 2006-08-02 |  |  | 2008-09-26 | [6 empty] | 2025-07-20 | [5 empty] | Terminated
53191003 | Gallup Skate Park | Gallup | McKinley | 321 East Historic Highway 66 | T15N R18W S15 | 35.5295 | -108.7387 | 0.9 | Lead in subsurface soil |  | City of Gallup | Morgan | 2019-10-16 | 2020-03-12 | 2021-05-22 |  | 2021-09-16 | 2022-03-17 |  |  | Completion report rec'd 27-MAR -23 | [8 empty] | Active
53181004 | Galles Chevrolet | Albuquerque | Bernalillo | 1301-1601 Lomas Boulevard Northeast | T10N, R3E, Sec 16 | 35.0917 | -106.627 | 8.7 | Petroleum hydrocarbons, volatile organic compounds, semi-volatile organic compounds, and metals |  | Sandia Foundation | Richards | 2008-08-14 | 2018-10-03 | 2018-10-12 |  |  | 2018-12-06 | 2018-12-18 | 2019-01-04 | 2019-04-05 | 2019-04-10 | [7 empty] | Closed
53011006 | G&G Auto | Farmington | San Juan | 701 E. 20th Street | T29N, R13W, Sec 10 | 36.7482 | -108.1969 | 3.26 | Chlorinated solvents and petroleum hydrocarbons. |  | McDonalds Corp. | Faris | 2001-03-05 |  |  |  | 2001-06-07 |  |  |  |  | 2001-08-29 |  |  |  |  | 2001-09-04 | 2014-12-05 |  | Closed
53031002 | First Federal Bank @ Digital | Albuquerque | Bernalillo | 4301 The 25 Way NE | T10N, R5E, Sec 13 | 35.1445 | -106.5964 | 1.279 | Chlorinated solvents. |  | First Federal Bank | Bynum | 2002-09-24 |  |  |  | 2002-12-05 |  |  |  |  | 2002-12-17 |  |  |  |  | 2002-12-18 |  |  | Closed
53221003 | Firestone Store 44W2 | Albuquerque | Bernalillo | 701 Central Ave NW | T10N R03E Sec20 | 35.5697 | -106.391 | 0.305 | TPH, VOCs & SVOCs in soil & soil vapor; VOCs, SVOCs, dissolved iron & manganese in groundwater |  | Presbyterian Healthcare Services | Morgan | 2022-03-31 | 2022-07-29 | 2022-08-09 |  | 2022-09-28 | 2022-11-16 |  | 2023-02-10 | 2025-01-22 |  | 2025-01-22 |  | none | none | 2025-01-22 |  |  | Closed CCOC
53071001 | Fina Truck Stop - Parcel "B" | Albuquerque | Bernalillo | 1901 Menual Blvd. NE | T10N, R3E, Sec 9 | 35.1092 | -106.6248 | 3.6 | Petroleum hydrocarbons in soil and ground water. |  | John Paloni | Muus | 2006-12-01 | 2007-03-09 | 2007-03-07 |  | 2007-04-12 | 2007-05-01 |  |  |  |  | 2008-04-15 |  |  | Continue remediation under the oversight of the Petroleum Storage Tank Bureau. |  |  |  | Active - CCOC
53071002 | Fina Truck Stop - Parcel "A" | Albuquerque | Bernalillo | 1901 Menual Blvd. NE | T10N, R3E, Sec 9 | 35.1092 | -106.6248 | 3.6 | Petroleum hydrocarbon from transgressing plume. |  | John Paloni | Shean | 2006-02-07 |  |  |  | 2007-04-12 |  |  |  |  | 2007-08-16 | [7 empty] | Closed
53051006 | Eubank Landfill - Northeast Fill Area | Albuquerque | Bernalillo | Located at south end of Eubank Ave SE | T10N, R4E, Sec 33 | 35.0541 | -106.5221 | 40 | Lead, volatile and semi-volatile organic compounds. |  | NM State Land Office | Shean | 2004-10-18 |  |  |  | 2005-04-06 |  |  |  |  | 2005-07-07 | [7 empty] | Closed
53141001 | Elite Laundry | Gallup | McKinley | 208 E. Historic Hwy 66 | T15N, R18W, Sec 15 | 35.5287 | -108.7398 |  | Chlorinated solvents |  | Elite Laundry Co. | Noger | 2014-04-30 | 2014-06-13 | 2014-06-21 |  | 2014-09-09 | 2014-10-22 | 2014-10-02 | 2014-11-24 | [9 empty] | Active
53171002 | El Castillo Norte | Santa Fe | Santa Fe | 401 Old Taos Highway | T17N, R9E, Sec 24 | 35.6927 | -105.9733 | 2.52 | naphthalene compounds in soils |  | Presbyterian Church USA | Cook | 2017-04-14 | 2017-04-18 | 2017-06-19 |  | 2017-08-30 | 2017-09-16 | 2018-02-18 | 2018-04-02 | 2018-09-10 | 2018-09-21 |  |  |  |  | 2018-11-14 |  |  | Closed
53211002 | Edible Arrangements | Santa Fe | Santa Fe | 825 Cerrillos Road | T17, R8E, Sec 26 (projected) | 35.6786 | -105.9514 | 0.18 | PCE and daughter products |  | FJC, LLC | Noger | 2024-03-07 | 2024-04-29 | 2024-06-08 |  | 2024-07-29 | 2024-07-29 | 2025-01-17 | 2025-03-04 | [9 empty] | Active
53121005 | Eagle Vista | Albuquerque | Bernalillo | E of Irving Blvd; W of Eagle Ranch Rd; S of The Aspens | T11N, R2E, Sec 7 | 35.1916 | -106.6644 | 6.771 | Chlorinated solvents, chromium. |  | Eagle Vista, LLC | Richards | 2012-09-17 | 2012-12-17 | 2012-12-28 |  | 2013-05-09 | 2013-05-13 | 18-Jun-2013; 15-Oct-18 | 20-Jun-13; 20-Nov-18 | 2020-02-28 |  | 2021-07-02 |  |  | Vapor barrier required for future buildings |  |  |  | Active-CCOC
53081001 | Duke City Distributing | Albuquerque | Bernalillo | 3203 Broadway SE | T10N, R3E, Sec 32 | 35.0467 | -106.6471 | 1.7235 | Petroleum hydrocorbons and heavy metals in soil and ground water. |  | Duke City Distributing, Lo. Inc. | Shean | 2007-11-13 |  |  |  | 2008-06-03 |  |  |  |  | 2008-07-02 |  |  |  |  | 17-Jul-08 |  |  | Closed
53081006 | Downtown @ 700-2nd | Albuquerque | Bernalillo | 700 2nd NW | T10N, R3E, Sec 17 | 35.0904 | -106.6478 | 0.729 | Petroleum hydrocarbons, chlorinated solvents. |  | Supportive Housing Coalition of New Mexico | Muir | 2008-08-13 | 2008-09-15 | 2008-10-14 |  | 2008-10-17 | 2008-10-28 | 2008-10-29 |  | 2008-10-29 | 2008-10-31 |  |  |  |  | 31-Oct-08 | 2008-12-18 |  | Closed
53181002 | Distribution Warehouse | Albuquerque | Bernalillo | 701 Comanche Road | T10N, R3E, Sec 4, NE 1/4 | 35.1255 | -106.625 | 8.7 | petroleum hydrocarbons; VOCs, heavy metals |  | GCB-1945, LLC | Muus | 2018-02-14 | 2018-05-04 | 2018-05-15 |  | 2018-07-11 | 2018-07-23 |  | 2018-11-09 | 2018-11-09 | 2019-01-14 | [7 empty] | Closed
53241004 | Deming West Side Project | Deming | Luna | West 1-10 & South 13th Street, 1200-1312 West Pine Street, and the vacated 12th Street between W. Pine and W. Spruce Streets | NW 1/4, NE 1/4, T23S, R9W | 32.2672 | -107.7744 | 3.91 | Petroleum Hydrocarbons |  | City of Deming/Allsups | Noger | 2024-07-26 | 2024-09-26 | 2024-10-08 |  | 2024-12-12 | 2024-12-13 | 2025-01-22 | 2025-03-04 | 2026-03-10 |  | 2026-04-09 |  | non-residential due to four separate active petroleum releases under PSTB oversight |  |  |  |  | Conditional closure/Active - CCOC
53021005 | Del Norte Gun Club | Sandoval County | Sandoval | Idalia Road @ NM 528 | T13N, R3E, Sec 36 | 35.3069 | -106.5841 | 56 | Lead shot - firing range. |  | Sandoval County | Muus | 2003-10-03 | 2002-04-26 | 2004-08-13 |  | 2003-10-03 | 2003-10-21 |  | 2005-12-06 | 2008-12-23 |  | 04/24/2009, 5/26/2009 |  | No development within 25-foot radius of asphalt capped area. | Deed restriction, asphalt cap over affected soils. |  |  |  | Active - CCOC
53221001 | Corky's Tractor Parts | Farmington | San Juan | 8301 E. Main St. |  | 36.4757 | -108.559 | 6.2 | petroleum hydrocarbons, RCRA metals in soil & groundwater |  | Corky's Tractor-Troy Harrison | Noger | 2022-01-04 | 2022-12-16 | 2023-03-17 |  | 2023-07-31 |  | 2023-08-28 | [10 empty] | Active
53021006 | Comet Cleaners @ Skyview | Albuquerque | Bernalillo | 1520 Tramway Boulevard NE | T10N, R4E, Sec 14 | 35.0961 | -106.4965 | 0.25 | Chlorinated solvents. |  | Clean Inc. | Faris | 2002-03-01 |  |  |  | 2003-04-25 |  |  |  |  | 2004-01-09 | [7 empty] | Closed
53161011 | College Plaza South - Unit 2404 | Santa Fe | Santa Fe | 2400 Cerrillos Road - Unit 2404 | T17N, R9E, Sec 34 | 35.6593 | -105.9806 | 6.48 | chlorinated solvents in soil vapor |  | B & LV College Plaza LP | Noger | 2016-11-04 | 2016-12-09 | 2016-12-25 |  | 2017-04-11 | 2017-04-28 | 2017-07-28 | 9/15/2017, 2/1/2021 | [9 empty] | Active
53021002 | Coca Cola Bottling Plant | Albuquerque | Bernalillo | 205 Marquette Avenue NE | T10N, R5E, Sec 13 | 35.0879 | -106.6447 | 3.25 | Petroleum hydrocarbons, chlorinated solvents. |  | Commercial Holding Co. | Bynum | 2001-08-13 |  |  |  | 2001-10-19 |  |  |  |  | 2002-03-05 |  |  |  |  | 2002-03-05 |  |  | Closed
53031001 | Casey Luna Ford | Belen | Valencia | 19381 North I-25 Business Loop | T5N, R2E Sec 6 | 34.6879 | -106.7675 | 5.59 | Petroleum hydrocarbons. |  | Casey and Beverly Luna | Muir | 2002-07-25 |  |  | 2009-12-11 | [13 empty] | Closed
53081007 | Casa Chevrolet | Albuquerque | Bernalillo | 7201 Lomas Blvd. | T10N, R4E, Sec 18 | 35.0875 | -106.567 | 6.5609 | Petroleum hydrocarbons. |  | Group 1 Automotive, Inc. | Muir | 2008-09-29 | 2008-12-29 |  |  | 2009-05-08 | 2009-05-14 |  |  | 2009-08-03 | 2009-08-21 | [7 empty] | Closed
53031005 | Capital Recycling | Albuquerque | Bernalillo | 2330 Second Street SW | T10N, R3E, Sec 29 | 35.0608 | -106.6529 | 2.13 | Petroleum hydrocarbons, asbestos. |  | BNSF Railway Co. | Muus | 2002-12-18 | 2004-01-13 | 2004-02-13 |  | 2004-04-07 | 2004-04-29 |  | 2004-08-25 | 2009-12-11 |  | 12/22/2010, 1/25/2010 |  | Land use restricted to non-residential. | Deed recordation noting presence of ACM in the disturbed zone. |  |  |  | Active - CCOC
53041002 | CAP XXX- Main & Reinken [McCasland Chevrolet] | Belen | Valencia | 315 North Main Street | T5N, R2E, Sec 18 | 34.663 | -106.7763 | 1.8 | Petroleum hydrocarbons. |  | CAP XXX - Main/Reinken, LLC | Muus | 2003-10-09 | 2003-11-07 | 2003-11-19 |  | 2004-01-07 | 2004-04-21 |  |  | 2004-06-29 |  | 2004-07-12 |  |  | PSTB Quarterly Monitoring Reports provided to VRP. | 2004-07-12 |  |  | Conditional closure/Active - CCOC
53044002 | CAP XXX - Main & McGaffey [Former Safeway] | Roswell | Chaves | 1200 South Main Street | T11S, R24E, Sec 9 | 33.3796 | -104.5232 | 2.04 | Petroleum hydrocarbons and PCE associated with transgressing plumes. |  | CAP II – Main/McGaffey, LLC | Shean | 2003-10-09 |  |  |  | 2004-01-07 |  |  |  |  | 2004-07-06 |  |  |  |  | 2004-07-12 | 2014-09-30 |  | Closed
53041006 | CAP II - G and G Auto | Farmington | San Juan | 701 East 20th Street | T29N, R13W, Sec 10 | 36.7482 | -108.1969 | 3.26 | Petroleum hydrocarbons. |  | CAP II - 20th/Butler, LLC | Muus | 2004-06-28 | 2004-07-20 | 2004-08-20 |  | 2004-09-24 | 2004-10-05 |  |  | 2004-10-25 |  | 2004-11-12 |  |  | PSTB Quarterly Monitoring Reports provided to VRP. | 2004-11-12 | 2014-12-05 |  | Conditional closure/Active - CCOC
53041003 | Caldwell Motors | Valencia County | Valencia | 322 North Main Street | T5N,R2E, Sec 15 | 34.6637 | -106.7752 | 0.37 | Petroleum hydorcarbons and heavy metals in soils. |  | Wells Fargo Bank New Mexico | Mariano | 2003-11-04 |  |  |  | 2004-05-20 |  |  |  |  | 2007-03-09 |  |  |  |  | 2008-03-07 |  |  | Closed
53103003 | Buena Vista Dairy (R-Qubed) | Mesquite | Doña Ana | 13085 Stern Drive | T25S, R3E, Sec 5 & 6 | 32.1597 | -106.6636 | 60.76 | Nitrate and dairy waste. |  | R-Qubed Energy, Inc. | Muus | 2010-05-18 | 2010-06-17 | 2010-07-01 |  | 2010-08-18 | 2010-09-22 | [5 empty] | 2018-12-24 | [5 empty] | closed-incomplete
53061005 | Broadway and Murray Site | Albuquerque | Bernalillo | 6501 Broadway Blvd SE | T9N, R3E, Sec 17 | 35.0043 | -106.6538 | 36.9707 | Nitrate in soils and ground water. |  | Anthony E. Giraudo and Patricia A. Giraudo | Cook | 2006-04-19 | 2006-06-10 |  |  | 2006-07-20 | 2006-08-25 | 2006-09-13 |  | 2006-09-13 |  | 2006-09-14 |  |  | Deed restriction, site drainage structures. | 2006-10-27 |  |  | Active - CCOC
53014001 | BNSF Carlsbad Depot Wye Track Area | Carlsbad | Eddy | 110 East Fox Street | T22S, R27E, Sec 6 | 32.425 | -104.225 | 57 | Petroleum hydrocarbons. |  | BNSF Railway Co | Mariano | 2001-03-14 |  |  |  | 2001-06-07 |  |  |  |  | 2004-03-01 | [7 empty] | Closed
53031003 | Beverly Hills Ave / San Mateo (Fidelity Trust) | Albuquerque | Bernalillo | No Street Address | T11N, R3E, Sec 12 | 35.1941 | -106.5855 | 2.5 | Solid waste, landfill gases. |  | Fidelity Trust Bank | Shean | 2002-11-18 |  |  |  | 2003-06-26 |  |  |  |  | 2003-12-01 |  |  |  |  | 2003-12-12 | 2010-09-08 |  | Closed
53031007 | Bell Trading Post property | Albuquerque | Bernalillo | 1503 Central Ave | T10N, R3E, Sec 18 | 35.0905 | -106.6644 | 1 | Lead in soils, asbestos. |  | City of Albuquerque | Shean | 2003-06-26 |  |  |  | 2003-12-23 |  |  |  |  | 2005-11-14 |  |  |  |  | 2005-11-14 |  |  | Closed
53065001 | Belen National Guard Armory J | Belen | Valencia | 715 South Main Street | T7N, R2E, Sec 20 | 34.6538 | -106.7794 | 4.5 | Iron and manganese in ground water. |  | NM Department of Military Affairs | Muir | 2006-04-20 |  |  | 2009-12-31 | [13 empty] | Closed
53034001 | Awtrey Enterprises | Clovis | Curry | 965A Humphrey Road | T2N, R36E, Sec 15 | 34.397 | -103.156 | 15 | Petroleum hydrocarbons. |  | Brett Johnson (505 Resources) | Mariano | 2002-12-19 |  |  |  | 2003-05-12 |  |  |  |  | 2004-09-12 | [7 empty] | Closed
53052001 | AT&SF Tie Treating Plant - Las Vegas | Las Vegas | San Miguel | Grand Avenue | T16N, R16E, Sec 26 | 35.5786 | -105.2158 | 20 | Zinc chloride. |  | BNSF Railway Company | Muir | 2006-03-02 | 2005-10-20 |  |  | 2006-03-08 | 2006-04-28 | 2008-09-17 |  | 2009-05-18 | 2009-05-18 | [7 empty] | Closed
53103002 | ASARCO Hop Canyon Site | Magdalena | Socorro | Former ASARCO Hop Canyon Site 1.2 miles S of Magdalena | T2S, R4W, Sec 34, 35 | 34.0929 | -107.2265 | 484.996 | Mining waste. |  | Asarco Multi-State Custodial Trust | Noger | 2010-04-05 | [16 empty] | Active
53043001 | ASARCO Deming Mill [Windblown Tailings] | Deming | Luna | County Road 394, circa one mile NW of Deming | T23S, R9W, Sec 20,21,29 | 32.2925 | -107.7827 | 54.43 | Lead and heavy metals. | NMMMD LU009RE | Asarco Incorporated | Muus | 2004-06-22 | 2004-07-16 | 2004-09-09 |  | 2004-10-20 | 2004-12-10 | 2007-09-11 | 2008-12-23 | 2013-10-21 |  | 2014-01-07 |  | Non-residential use due to As. | Restrictive covenant to restrict land use to non-residential. | 2014-06-13 |  |  | Active - CCOC
53171007 | Arnie's Cleaners | Albuquerque | Bernalillo | 8217 Menaul Blvd. NE |  | 35.1095 | -106.5523 | 0.2066 | PCE, TCE, and daughters in soil vapor |  | Thu-Trang Nguyen | Noger | 2017-08-21 | 2017-12-15 | 2018-01-05 |  | 2018-03-28 | 2018-04-24 | 2018-03-30 | 2018-04-20 | 2026-01-07 |  | 2026-02-12 |  | yes, non- residential land use only due chlorinated solvents above residential standards in soil vapor | non-residential |  |  |  | Conditional closure/Active - CCOC
53191002 | Angel Fire- LeBus | Angel Fire | Colfax | Intersection of Hwy 64 and Mountain View Blvd. | 1T, 25N, R15E, Sections 150, 167, 168 | 36.4305 | -105.2944 | 78.6 | creosote (PAHs), VOCs, SVOCs, & RCRA metals in groundwater, soil |  | Angel Fire, LLC | Morgan | 2019-06-26 | 2021-09-10 | 2021-10-14 |  | 2022-02-09 | 2024-09-05 | 2026-04-01 | [10 empty] | Active
53061003 | Americus Mechenbier | Bernalillo County | Bernalillo | SE Corner of San Mateo Blvd and Venice Ave | T11N, R3E, Sec 12 | 35.196 | -106.5863 | 6.04 | Muncipal solid waste. |  | Americus L.L.C. | Shean | 2005-08-04 |  |  |  | 2007-02-09 |  |  |  |  | 2009-08-03 |  |  |  |  | 2009-08-05 |  |  | Closed
53231002 | American Pride Cleaners | Albuquerque | Bernalillo | 1349 San Mateo SE | T10N R3E Sec 26 | 35.0604 | -106.5876 | 0.29 | Chlorinated solvents |  |  | Morgan | 2023-03-23 | 2023-07-31 | 2024-01-01 |  | 2024-05-28 | 2024-06-04 | 2024-09-04 | 2024-09-30 | [9 empty] | Active
53161007 | Albuquerque Railyards | Albuquerque | Bernalillo | 1100 2nd Street SW (2nd and Commercial) | T10N, R3E, Sec 20, 29 | 35.0746 | -106.6501 | 27.32 | soil: metals, PAHs, petroleum hydrocarbos, LNAPL Soil vapor: VOCs groundwater: metals, naphthalenes; EDB buildings: ACM/LBP |  | City of Albuquerque | Morgan | 2019-01-17 | 2019-03-05 | 2019-03-29 |  | 2019-05-25 | 2019-06-05 | 0 | 14-Aug-20 (ABQ Rail Yards north and south VRP Work Plans) | 4/28/21 (ABQ Rail Yards North Only) |  | 9/28/2021 (ABQ Rail Yards North) |  | Yes, residential land use restricted to areas where contaminant levels are below NMED standards | Soil Management plan shall be followed during redevelopment/construction, Annual groundwater monitoring, Annual soil vapor monitoring, Future and existing building shall have vapor intrusion mitigation system if contaminants exceed VISLs, Asbestos and lead based paint shall be removed of and diposed of according to state regulations prior to demolition, Asbestos and lead based paint shall be immobilized or contained prior to rennovation, Residential land use only allowed in areas where contamination is below NMED standards, Interim uses allowed if they are consistent with uses outlined in the approved VRP Work Plan |  |  |  | Active
53081005 | Albuquerque Locomotive Shops (formerly BNSF-CWE) | Albuquerque | Bernalillo | 2nd & Bridge Sts | T10N, R3E, Sec 29 | 35.07 | -106.65 | 28 | Petroleum hydrocarbons, metals, asbestos. |  | City of Albuquerque | Furmall | 2008-07-11 | [16 empty] | Closed
53131003 | Albuquerque First Baptist Church | Albuquerque | Bernalillo | 101 Broadway Blvd NE | T10N, R3E, Sec 20 | 35.0847 | -106.6457 | 6.96 | Petroleum hydrocarbons. |  | First Baptist Church | Furmall | 2013-11-01 | 2014-02-18 | 2014-02-28 |  | 2014-06-06 | 2014-06-06 | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-27 |  |  |  |  | 9-Jul-14 | 2015-12-11 |  | Closed
53121002 | Albuquerque Airpark Partners Property | Albuquerque | Bernalillo | 2901 Transport St SE and adjoining tract to south |  | 35.0526 | -106.6363 | 16.78 | Lead in soil, volatile organic compounds in ground water. |  | John Lorentzen | M. Hunter | 2012-03-13 | 2012-08-03 | 2012-08-13 |  | 2012-12-28 | 2013-01-22 | 2013-01-04 | 2013-01-28 | 2013-02-21 | 2013-04-09 |  |  |  |  | 2014-03-28 |  |  | Closed
53241005 | ABQ Cleaners | Albuquerque | Bernalillo | 3002 Monte Vista Blvd. NE | T10N, R3E, Sec 22 | 35.0812 | -106.6119 | 0.085 | Chlorinated solvents |  | Fetherolf, LLC | Morgan | 10/1/2024; 1/17/2025 rev1 |  | 2025-03-27 |  | 2025-05-05 | [6 empty] | 2025-10-23 | [5 empty] | Terminated
53161005 | A.C. Houston Lumber site | Gallup | McKinley | 104 North Second Street | T16N, R15W, Sec 18 | 35.5294 | -108.7425 | 6.8 | petroleum hydrocarbons, esp. BTEX and naphthalene in groundwater |  | AC Houston Lumber - Gordon Barclay | Noger | 2016-05-13 | 2016-07-08 | 2016-08-22 |  | 2016-11-10 | 2016-12-05 | 2019-05-07 | 2019-05-25 | [9 empty] | Active
53011004 | 997 Old Coors Road | Albuquerque | Bernalillo | 997 Old Coors Road | T10N, R2E, Sec 26 | 35.0696 | -106.6998 | 1.25 | Petroleum hydrocarbons. |  | Dennis Romero | Bynum | 2001-02-15 |  |  |  | 2001-05-16 |  |  |  |  | 2002-01-17 |  |  |  |  | 2002-01-17 |  |  | Closed
53161008 | 9220 Broadway SE | Albuquerque | Bernalillo | 9220 Broadway SE | T9N, R3E, Sec 31 | 34.9593 | -106.6597 | 9.7 | nitrate, chloride, sulfate in soil and groundwater |  | Storage Systems, LLC | Cook | 2016-08-19 | 2016-10-05 | 2016-10-27 |  | 2016-12-19 | 2017-01-10 | 2017-01-14 | 2017-01-20 | 2017-01-26 | 2017-05-26 | [7 empty] | Closed
53141003 | 8201 E Main St (former General Crude) | Farmington | San Juan | 8201 E Main St | T30N, R12W, Sec 21 | 36.7935 | -108.0967 | 12.45 | Petroleum hydrocarbons, esp. BTEX and naphthalene, PCE in soils; EDC, iron, manganese, boron in ground water |  | Desert Sun Investments, LLC | Noger | 2014-06-16 | 2014-08-12 | 2014-08-27 |  | 2014-10-31 | 2014-12-05 | 2015-01-27 | 2/13/2015, 4/1/2020 | [9 empty] | Active
53141007 | 500 Copper Square Building | Albuquerque | Bernalillo | 500 Copper Ave NW |  | 35.0856 | -106.653 | 0.6 | Chlorinated solvents and petroleum in soil, soil vapor, and ground water |  | First Financial Credit Union | M. Hunter | 2014-10-29 | 2014-12-08 | 2014-12-19 |  | 2015-03-06 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-07-01 | 2015-08-12 | [7 empty] | Closed
53121001 | 4102 Broadway SE | Albuquerque | Bernalillo | 4102,4110,4118,4126 El Rey SE | T9N, R3E, Sec 8 | 35.0191 | -106.644 | 15.37 | Nitrate, sulphate, total dissolved solids, chloride. |  | Albert Lemieux, Broadway LLC and Scott Whittington, El Rey Industrial LLC | Cook | 2011-09-23 | 2011-12-07 | 2011-12-01 |  | 2012-02-02 | 2012-04-13 | 2012-06-19 | 2012-08-14 | 2017-08-11 |  | 2017-09-18 |  | non-residential land use |  | 2017-10-02 |  |  | Active - CCOC
53231007 | 401 Menaul | Albuquerque | Bernalillo | 401 Menaul Blvd. NW | T10N, R3E, Sec 8 | 35.1115 | -106.6471 | 1.4895 | TPH and chlorinated hydrocarbons |  | 401 Menaul LLC | Noger | 2024-01-17 | 2024-04-18 |  |  | 2024-07-29 | 2024-07-29 | 2024-06-21 | 2024-09-04 | 2024-09-29 | 2024-09-30 | [7 empty] | Closed
53181001 | 301 N. Main | Belen | Valencia | 301 N. Main |  | 34.6631 | -106.7765 | 0.5 | petroleum hydrocarbons in soil and groundwater |  | WSCI LLC | Cook | 2018-01-10 | [10 empty] | 2018-11-07 | [5 empty] | Closed
53211004 | 300-312 Central SE Properties | Albuquerque | Bernalillo | 300-312 Central SE Properties | T10N R3E Sec 20 | 35.0834 | -106.6443 | 0.23 | VOCs (PCE & TCE) |  | Hayman Properties, LLC | Noger | 2021-12-03 | 2022-01-20 | 2022-02-03 |  | 2022-03-31 | 2022-05-10 | 2022-09-16 | 2023-04-03 | [9 empty] | Active
53161010 | 2917 Juan Tabo NE | Albuquerque | Bernalillo | 2917 Juan Tabo NE | T10N, R4E | 35.1157 | -106.5161 | 0.445 | chlorinated solvents in soil vapor |  | Russell K Whitener Irrovocable Trust | Cook | 2016-11-19 | [10 empty] | 2017-05-26 | [5 empty] | Closed
53141002 | 247 Plaza Park | Las Vegas | San Miguel | 247 Plaza Park | T16N, R16E, Sec 27 | 35.5919 | -105.2271 | 0.1 | migrating petroleum hydrocarbon plume; benzo(a)pyrene above SSL |  | BRE-2, Inc. | Furmall | 2014-05-30 | 2014-07-18 | 2014-07-27 |  | 2014-09-09 | 2014-10-17 | 2014-10-13 | 2014-10-31 | 2014-10-31 | 2014-11-18 |  |  |  |  | 2015-01-09 |  |  | Closed
53121004 | 201 E. Coal Avenue | Gallup | McKinley | 201 E. Coal Avenue | T15N, R18W, Sec 15 | 35.5283 | -108.7398 | 0.5 | Chlorinated solvents in ground water and soil vapor. |  | Community Area Resource Enterprise, Inc. | Muus | 2012-07-09 | 2012-10-09 | 2012-10-23 |  | 2013-05-07 | 2013-05-14 | 2013-08-01 | 2013-08-01 | [9 empty] | Active-CCOC
53251003 | 1710 Llano St. | Santa Fe | Santa Fe | 1710 Llano Street, Santa Fe | T17N, R9E, Section 34 | 35.6582 | -105.9731 | 0.3 | chlorinated solvents |  | TP SMVW, LLC c/o Forrest Thomas | Noger | 2025-02-19 |  | 2025-05-22 |  | 2025-06-24 | 2025-06-24 | 2025-07-17 | 2025-09-11 | [9 empty] | Active
53093001 | 1555 & 1565 West Picacho Avenue | Las Cruces | Doña Ana | 1555 & 1565 West Picacho Avenue | T23S, R1E, Sec 13 | 32.3119 | -106.7995 | 1.34 | Diesel and lead. |  | Russell Johnson | Muus | 2008-10-20 | 2009-03-06 | 2009-04-03 |  | 2009-07-10 | 2009-08-12 | 2009-02-09 |  | 2009-12-04 |  | 2010-03-04 |  | Land use restricted to non-residential. | Concrete pad over contaminated soil. |  |  |  | Active - CCOC
53101001 | 1501 12th St NW | Albuquerque | Bernalillo | 1501 12th St NW | T10N, R3E, Sec 18 | 35.1019 | -106.6584 | 1.47 | PCE in groundwater |  | Coe Properties | Furmall | 2009-11-18 | 2010-09-10 | 2011-02-19 |  | 2013-07-26 | 2013-08-23 | 2010-01-29 | 2013-07-26 | 2013-09-18 | 2013-11-06 |  |  |  |  | 2014-02-21 |  |  | Closed
53221004 | McAnally Site - RACI | Berino | Dona Ana | 415 San Benito Road | T26S, R3E, 1/4NW, 1/4SE | 32.0718 | -106.6215 | 250 | Nitrates, Total dissolved solids, chloride, and sulfate in groundwater |  | RACI Management Company, Inc. | Morgan | 2022-07-20 | [16 empty] | Active
53241002 | San Antonio Spear D LLC | San Antonio | Socorro | 1632 NM-1, 35 San Antonito Rd, 3 Zanja Rd, 1 Zanja Rd | T5S, R1, Section 8 | 33.8951 | -106.868 | 9.16 | Barium and Lead in soil, channel sediment, and groundwater |  | Spear D, LLC | Richards | 2025-07-29 |  |  | 2026-04-10 | [13 empty] | Rejected
53191001 | 110 Gold Ave | Albuquerque | Bernalillo | 110 Gold Ave SE | T10N/R3E/Section 20 | 35.0826 | -106.6457 | 0.4 | TBD |  | KLG 30, LLC | Muus | 2019-04-24 | 2019-11-07 | 2019-12-01 |  | 2020-05-18 | 2021-02-10 | 2019-07-30 | 2020-05-18 | 2022-02-11 |  | 2023-05-08 | [6 empty] | closed
53261001 | La Unica No. 2 | Santa Fe | Santa Fe | 1932 Cerrillos Road, Santa Fe | T17N, R9E, Section 34 | 35.6632 | -105.9751 | 0.44 | chlorinated solvents (PCE & TCE) |  | La Unica No. 2, Jorge Lopez | Noger | 2026-04-13 | [16 empty] | Active
Total | [7 empty] | 6774.7879 | [21 empty] | 164