## Slide 1: New Mexico Environment Department
Water & Natural Resources Committee
Kelsey Rader, Deputy Division Director, Water Protection Division
Miori Harms, Uranium Mine Reclamation Coordinator, Office of Strategic Initiatives
October 29, 2025
Neglected Contaminated Sites and
Abandoned Uranium Mine
Remediation Funding Update

## Slide 2: Spend Plan Update
$20M Special Appropriation:
  $2M for contract support to identify potential responsible parties and take appropriate legal action.
  $6M for cleanup of Tucumcari Truck Terminal and the former Aerex Refinery in San Juan County.
  $12M to address uranium mine sites with no responsible party and where the site is not eligible for cleanup under other state or federal programs.

## Slide 3: Contaminated Sites Update
$6M for cleanup of Tucumcari Truck Terminal and the former Aerex Refinery in San Juan County.
  Tucumcari Truck Terminal soil and groundwater contaminated with petroleum wastes; hazardous building materials (asbestos, lead-based paint)
  Contractor: Daniel B. Stephens and Assoc.
  Timeline
    Oct.-Nov. 2025: soil investigation
    Dec. 2025: hazardous building materials abatement
    Feb.-March 2026: contaminated soil excavation
Notes: Aerex site extent of soil contamination is well defined, so we can move directly to soil remediation. TTT has known soil contamination, but the extent needs to be better defined before a work plan and cost estimate for soil remediation can be developed (hence the soil investigation to be conducted first).

## Slide 4: Contaminated Sites Update
$6M for cleanup of Tucumcari Truck Terminal and the former Aerex Refinery in San Juan County.
  Aerex Refinery soil and groundwater contaminated with petroleum wastes
  Contractor: EA Engineering, Science, and Technology.
  Timeline:
    Nov.-Dec. 2025: Remedial Action Plan preparation.
    March-May 2026: Contaminated soil excavation.
Notes: Primary reason for time lag between RAP development and soil excavation is to allow a 30-day public comment period.

## Slide 5: Uranium Mine Update
$12M to address abandoned uranium mine sites.
  Six cleanup contractors hired for Grants Mining District.
    EA (a public benefit company), INTERA, and ENTACT will be breaking ground this fiscal year on the Schmitt Decline, Moe No. 4, and Red Bluff No. 1 mines.
    Tetra Tech, Parsons, and Engineering/Remediation Resources Group-Los Alamos Technical Associates–Joint Venture preparing sites for cleanup next FY.
  The contracts are all 4 years, which is an approximate timeline to conduct cleanup.
Notes: Caveat: We are hoping to close one mine this year (Schmitt Decline), but I can't make any promises since we are still figuring out what needs to be done. It is typical for permitting alone to take 2 years. We are fast-tracking the three sites mentioned, but it is a lot of coordination between DCA/SHPO, NMSLO, EPA, EMNRD-MMD to get it all done. We are finding a lot of cultural resources on the sites that cannot be touched.

## Slide 6: Neglected Uranium Mine Cleanups
Grants Mining District
Lost Mine
T-20 Mine
Schmitt Decline Mine
Red Bluff No. 1 Mine
Moe No. 4 Mine
Tentative
Grants
Milan
Thoreau
Laguna Pueblo
NMED Uranium Mine Dashboard: Formerly Operating Uranium Mine and Mill Site in New Mexico

## Slide 7: Moe No. 4 Uranium Mine
Approximately $4M for surface reclamation
  Contractor: INTERA Inc.
  Timeline:
    May-June 2026: Reclamation and site closeout.

## Slide 8: Schmitt Decline Uranium Mine
Approximately $1.9M for surface reclamation
  Contractor: EA Engineering, Science, and Technology, Inc., PBC (“EA”)
    March-June 2026: Reclamation and site closeout.

## Slide 9: Red Bluff No. 1 Uranium Mine
Approximately $1.2M for surface reclamation
  Contractor: ENTACT LLC
    March-June 2026: Reclamation and closeout.
Site is located on the edge of a bluff, showing exposed ore-bearing formation (gray rock).
It is a dry mine (no groundwater impact) located on state trust land.

## Slide 10: Next Steps
There are over 348 (= 302 + 46) sites in New Mexico without a responsible party:
  302 neglected contaminated sites plus an unknown number of former dry cleaner sites.
  46 neglected abandoned uranium mine sites.
  Consider a sustainable funding for site remediation which helps protect and revitalize communities.
Notes: GWQB compiled an inventory of approx. 1600 dry cleaner locations across the state. Sampling to date at a subset of dry cleaner locations (65 sites) has been conducted; approx. 20% of the tested sites have soil vapor concentrations of dry cleaning chemicals above health-based screening levels. It is possible that there may be more than 100 former dry cleaner locations that require remediation to address contaminants in soil vapor. This number will increase as RPs run out of money (become non-viable RPs). For example, the Section 12 mine cleanup led by MMD will bankrupt the Trust before they can conduct all cleanup. The Tronox mine settlement is expected to run out of funds before cleanup is completed on all the sites. The cost of cleanup has increased significantly since the settlement, so time is not on our side. We are in communication with EPA's Office of Deserts, Mountains and Plains on finding a Good Samaritan site. Unfortunately, the pilot program is new and must go through procedures development process, is limited to 15 low-risk sites, sunsets in 12 years, and requires an NGO that is willing to fund the cleanup. I would recommend the legislature appropriate funds into the Uranium Mine Reclamation Revolving Fund so we can stand up a sustainable program with a known budget.